## Sprint Plan
⚡ BROADCASTBRAIN — HACKATHON SPRINT PLAN v2
3-Feature Build (SPEC_v2.md) ¦ Team of 4 Generalists ¦ 22hr Hack ¦ Stack: RN + Expo + Cactus RN + Gemma 4 Multimodal
PHASE | SPRINT | TIME | TRACK A — GEMMA 4 | TRACK B — DATA | TRACK C — AUDIO/PIPELINE | TRACK D — UI/DEMO | MILESTONE
PRE-KICKOFF 10 AM–1 PM | SPRINT 0 De-Risking | 10 AM–1 PM Day 1 | • Clone github.com/cactus-compute/cactus, follow README setup • Run `cactus build --python` on Mac, verify • Goal: get Gemma 4 producing ONE token — proves on-device works • Spike Cactus RN SDK — does it expose Gemma 4 multimodal in JS? If no, plan Expo config plugin route • Read docs.cactuscompute.com + Gemma 4 blog post end-to-end | • Sign up at developer.sportradar.com (MLB trial v7) • Wait for API key email, test one curl • Pick the demo game: specific Mets vs Phillies date with audio clip available • Download 3 MLB broadcast clips (Mets radio on YouTube) — trim to 30s — these are the dev fixtures | • `npx create-expo-app broadcastbrain` • Install expo-av, expo-speech, zustand, tamagui/nativewind • Push to GitHub, branch protection • Get a physical iPhone onto the build laptop: signed in, dev mode on, trusted • Verify `npx expo run:ios` to physical device works end-to-end | • Design warmup: import SPEC_v2 UX rules into Figma • Reference Pat McCarthy 1-pager aesthetic (dark navy + orange accent) • Sketch the 3 primary screens — SpottingBoard, LiveDashboard, VoiceQuery states • Confirm React Navigation structure, set up tamagui theme tokens | ✅ Cactus + Gemma 4 proven ✅ Sportradar key in hand ✅ iPhone demo device ready ✅ Repo scaffolded
HARD PUSH 🔥 Day 1 | SPRINT 1 Foundations | 1–3 PM | • Wrap Cactus into the single contract: `askGemma(input, context, routing) → Promise<Result>` • Input accepts {prompt} OR {audio: ArrayBuffer} • Prove Gemma 4 multimodal: send an audio chunk, get back a transcript • Prove function calling: define one function `get_player_stat`, have Gemma 4 call it • Commit the function toolbox skeleton (see SPEC_v2 §Feature 3 signatures) | • Fetch Mets + Phillies full rosters from Sportradar (2 calls, cache immediately) • Fetch season stats + last-10-game splits per player • Hit rate limits carefully: 1 req/sec, 1000 req/month — budget this • Output: `assets/game_cache.json` with ~50 players, full stat blocks • Commit bundled cache so everyone can pull | • expo-av microphone capture: 2s rolling windows, 500ms overlap • Energy gate (RMS threshold ~0.01) — skip silence • Output: callback stream of audio ArrayBuffers • Test on device using the Mets clip played through speaker into mic • Logs the timestamp of every chunk — needed later for latency measurements | • Build the Zustand event bus: stat_card / transcript / context / voice_query events • Scaffold 2 screens: SpottingBoardScreen + LiveDashboardScreen • Dummy data: render a fake LiveStatCard that receives mock events every 3s • Apply the dark theme from Figma — get the aesthetic right early, don't wait | ✅ All 4 tracks unblocked ✅ askGemma returns from real Gemma 4 ✅ Audio chunks flowing
HARD PUSH 🔥 Day 1 | SPRINT 2 Feature 1: Spotting Board | 3–5 PM | • Implement the spotting-board prompt (SPEC_v2 §Feature 1) • For each player: { stats_json, matchup } → { top_stats[3], storyline, matchup_note } • Test on 5 real Mets hitters — outputs must be concise, natural • Budget 1 hr of prompt iteration — this is your first real tuning cycle • Rule: if Sportradar field missing, output '—', never guess | • Pipeline: walk `game_cache.json` → call askGemma per player → store result • Generate `spottingboard.json` bundle with all ~50 players + generated spotlights • Commit this artifact — app ships with it pre-baked (works airplane mode) • Bonus: generate a PDF export helper for the paper-backup demo moment | • Pause live pipeline work — wait for Track A to stabilize • Meanwhile: build the orchestrator skeleton `pipeline.ts` (audio → askGemma → event bus) • Write the dup-suppression scaffold: track STT output, don't re-surface spoken stats | • PlayerCard component: headshot, #/pos/name, 3 stat lines, storyline, matchup note, Sportradar ✓ badge • SpottingBoardScreen grid: home (left) ¦ away (right), scroll per side • Tap-to-expand for full season line, last 10 games, splits • Dark theme, big tabular numerals, peripheral-vision-friendly sizing | ✅ Feature 1 renders on iPhone in airplane mode with 50 players + source badges
HARD PUSH 🔥 Day 1 | SPRINT 3 Feature 2: Live Stat Whisper | 5–7 PM | • Build the live pipeline Gemma 4 prompt (SPEC_v2 §Feature 2) • Single multimodal call: audio → {transcript, player, event, situation, stat_opportunity, query_complexity} • Wire function toolbox: get_player_stat, get_team_stat resolve against game_cache.json • Final step: Gemma 4 generates stat_text with source + confidence • Must be ONE call (not STT → separate LLM) — this is the technical integration story | • Expose `get_player_stat(player, situation)` as a JS function Gemma 4 can call • Fuzzy-match player name against cache (spelling variants: Soto, J. Soto, Juan Soto) • Add situational filters: RISP, vs LHP, vs RHP, last 10, home/away • Return { stat_text, stat_value, source: 'Sportradar', confidence } • Resolve in <20ms (all in-memory) | • Full live pipeline: audio chunk → askGemma (with function toolbox) → emit stat_card event • Measure latency per stage, log it: audio_ms / gemma_ms / fn_ms / render_ms • Dup suppression: Gemma 4's transcript output feeds a 'recently spoken' buffer — skip stat if already said • Run 5 MLB fixtures end-to-end on device | • LiveStatCard component with fade-in animation (<300ms) • FlashingCue: orange pulse ~1Hz top-right on new stat • LatencyCounter: tiny bottom-right, shows real measured ms • Medium-confidence state: '~' prefix, amber tint, never spoken • LiveDashboardScreen binds to event bus | ✅ Feature 2 demo-ready: MLB audio → stat on screen <1.5s on iPhone, airplane mode
HARD PUSH 🔥 Day 1 | SPRINT 4 Feature 3: Voice Query | 7–9 PM | • Build the voice-query prompt: transcript → reason about intent → function-call toolbox → answer • Add `get_historical(player, comparison)` function (may route to Gemini) • Add the 'I don't have verified data on that' escape: if no function grounds the answer confidently • Enforce: spoken answers must be confidence=high only (medium never TTS'd) • Run 10 real-world test questions end-to-end | • Extend function toolbox: get_team_stat, get_historical, get_game_context • Add a 'situation' field parser — Gemma 4 says 'vs lefties' → filter cache accordingly • Decide which queries must hit Gemini (cloud route) vs pure local • Hard rule for demo: all demo questions must be answerable locally (airplane mode) | • Press-to-talk capture (up to 8s): hold button → record → release → pipe to askGemma • Wire expo-speech for opt-in TTS reply on high-confidence answers • Haptic feedback on button press/release • Timeout guardrails: auto-stop at 8s, cancel in-flight query on new press | • VoiceQueryButton (big bottom-of-screen, press-to-talk with haptic) • Listening state: waveform animation + 'Listening…' • Thinking state: shimmer + 'Thinking…' • AnswerCard: user's question at top, sourced answer below, TTS indicator • 'I don't have verified data' state — confident not apologetic | ✅ Feature 3 demo-ready: button → question → sourced answer on screen + spoken <2s
HARD PUSH 🔥 Day 1 | SPRINT 5 First Dry Run | 9–11 PM | • Prompt tuning marathon: run all MLB fixtures through each feature's pipeline • Tighten stat_text brevity (max 15 words), player-name echo suppression • Build a tiny eval harness: 10 inputs → expected outputs, rerun on each prompt change • Latency check: if >1.5s on iPhone, profile and shave | • Running score tracker (Bob Heussler ask): compute scoring runs over rolling window from cached PBP • Story reminder queue (Rich Ackerman ask): bullet list input, STT tracks what's been said • Milestone/streak alerts (Trey Redfield ask): pre-compute active streaks, flag at-risk at-bats | • End-to-end dry run: airplane mode on, play Mets clip, watch every piece fire • Log latencies for every run — get the average to put in the pitch • Test all 3 features back-to-back without restarting the app • Fix any integration breakage discovered | • Dark theme polish: typography pass, spacing pass, accent color hits • Make sure airplane mode indicator is visible in every screen (iOS status bar) • Latency counter placement — small but legible on stage mirror • One 'hero' frame per feature — screenshot for submission deck | ✅ Full 5-min demo script runs end-to-end in airplane mode
BUFFER Day 1 | TEAM SYNC | 11 PM–12 AM | Fix P0 blockers only | Fix P0 blockers only | Fix P0 blockers only | ALL TEAM: Full demo run-through together · identify crashes · document P0/P1/P2 bugs · decide overnight sleep shifts · commit + push all branches · eat + hydrate | 🔄 Team aligned P0 list documented Sleep shifts set
SLOW BURN 🌙 Overnight | SHIFT A (2 devs) | 12–4 AM | • Continue prompt iteration against overnight failure cases • If pipeline stable: sleep | • Pre-cache a backup game in case primary is rain-delayed / unavailable • Validate all stats manually against Sportradar for 5 hero players | • Fix any P0 from sync • Improve latency further if still >1s on iPhone | • Polish animations, haptic feedback timing, color tokens • Record a backup demo video (silent) in case live demo fails • Sleep if UI is stable | 🌙 Shift A objectives: • P0 bugs fixed • Backup video exists • Backup game cached
SLOW BURN 🌙 Overnight | SHIFT B (2 devs) | 4–8 AM | • Pickup from Shift A's eval runs, continue tuning weakest prompt • Edge cases: low-confidence paths, Gemini cloud routing fallback | • If time: load a second game's worth of data for the 'this generalizes' pitch beat | • Run 20 more dry-run cycles · record latency distribution · that number goes in the pitch deck • Final integration testing on physical iPhone | • Record backup demo video WITH audio narration (insurance if stage mic dies) • Upload to Drive, share with whole team | 🌙 Shift B objectives: • Latency p50/p95 documented • Audio backup video exists • All P0s closed
FINAL PUSH Day 2 | SPRINT 6 Demo Polish | 8–10 AM | • Feature freeze. No more prompt changes unless critical • Verify function toolbox is locked | • Verify 100% of stat cards carry Sportradar ✓ • No hallucinated stats — spot-check 20 random cards | • Full dry run #1: timed, phone-only, airplane mode, no keyboard touches • Full dry run #2: same • Full dry run #3: same, by a different team member (stress test) | • Final deck: 1 problem slide + 3 feature screens + latency number + Pat McCarthy quote • Submission form: description, tagline, demo video link, team names • Upload backup demo video + spotting board PDF to submission | ✅ 3 clean dry runs complete ✅ Deck final ✅ Submission draft ready
FINAL PUSH Day 2 | SPRINT 7 Submission | 10–11 AM | ALL: Final rehearsal with stage setup (device + mirror) ¦ Assign speaking parts per team member (60s each) ¦ Kill-the-WiFi moment rehearsed ¦ Submit BEFORE 10:55 AM, not at 11:00 AM ¦ Breathe |  |  |  | 🏆 SUBMITTED 11:00 AM sharp

## Task Backlog
📋 TASK BACKLOG — Checklist Format (tick as you ship)
# | TRACK | SPRINT | TASK | OWNER | DONE?
1 | A | Sprint 0 | Clone cactus-compute/cactus repo and follow README setup end-to-end |  | ☐
2 | A | Sprint 0 | Run `cactus build --python` — Gemma 4 produces at least one token |  | ☐
3 | A | Sprint 0 | Spike Cactus RN SDK: does it expose Gemma 4 multimodal audio input in JS? |  | ☐
4 | A | Sprint 0 | Read docs.cactuscompute.com + Gemma 4 blog end-to-end |  | ☐
5 | B | Sprint 0 | Sign up at developer.sportradar.com (MLB trial v7), receive API key |  | ☐
6 | B | Sprint 0 | Pick specific Mets vs Phillies demo game (date + audio clip on YouTube) |  | ☐
7 | B | Sprint 0 | Download 3 MLB broadcast fixtures, trim to 30s each |  | ☐
8 | C | Sprint 0 | `npx create-expo-app broadcastbrain` + install deps (expo-av, expo-speech, zustand) |  | ☐
9 | C | Sprint 0 | Physical iPhone: signed in, dev mode on, trusted on build laptop |  | ☐
10 | C | Sprint 0 | Verify `npx expo run:ios` ships app to device |  | ☐
11 | D | Sprint 0 | Import SPEC_v2 UX rules into Figma; sketch 3 primary screens |  | ☐
12 | D | Sprint 0 | Confirm navigation structure, tamagui theme tokens |  | ☐
13 | A | Sprint 1 | Wrap Cactus into `askGemma(input, context, routing)` contract |  | ☐
14 | A | Sprint 1 | Prove Gemma 4 multimodal: audio in → transcript out |  | ☐
15 | A | Sprint 1 | Prove function calling: define get_player_stat, Gemma 4 invokes it |  | ☐
16 | B | Sprint 1 | Fetch Mets + Phillies full rosters + season stats → game_cache.json |  | ☐
17 | B | Sprint 1 | Aggressive caching layer (never re-hit Sportradar during dev) |  | ☐
18 | B | Sprint 1 | Commit assets/game_cache.json ~50 players with full stat blocks |  | ☐
19 | C | Sprint 1 | expo-av 2s rolling mic capture with 500ms overlap + silence gate |  | ☐
20 | C | Sprint 1 | Test capture on device with Mets clip played through speaker |  | ☐
21 | D | Sprint 1 | Zustand event bus: stat_card / transcript / context / voice_query |  | ☐
22 | D | Sprint 1 | Scaffold SpottingBoardScreen + LiveDashboardScreen |  | ☐
23 | D | Sprint 1 | Dummy LiveStatCard receives mock events every 3s |  | ☐
24 | D | Sprint 1 | Apply dark theme tokens from Figma |  | ☐
25 | A | Sprint 2 | Spotting-board prompt: {stats, matchup} → {top_stats, storyline, matchup_note} |  | ☐
26 | A | Sprint 2 | Tune prompt against 5 real Mets hitters; outputs concise + natural |  | ☐
27 | A | Sprint 2 | Missing-data rule: output '—' when Sportradar field absent |  | ☐
28 | B | Sprint 2 | Walk game_cache.json → askGemma per player → spottingboard.json |  | ☐
29 | B | Sprint 2 | Generate PDF export of spotting board for paper backup |  | ☐
30 | C | Sprint 2 | Orchestrator skeleton pipeline.ts (audio → askGemma → events) |  | ☐
31 | C | Sprint 2 | Dup-suppression scaffold (track STT, don't re-surface spoken stats) |  | ☐
32 | D | Sprint 2 | PlayerCard component: headshot, #/pos/name, 3 stats, storyline, matchup |  | ☐
33 | D | Sprint 2 | Sportradar ✓ source badge on every stat |  | ☐
34 | D | Sprint 2 | SpottingBoardScreen: split-grid home/away, scroll per side |  | ☐
35 | D | Sprint 2 | Tap-to-expand player → full season line, last 10, splits |  | ☐
36 | A | Sprint 3 | Live pipeline prompt: audio → {transcript, context, stat_opportunity} |  | ☐
37 | A | Sprint 3 | Wire function toolbox resolving against game_cache.json |  | ☐
38 | A | Sprint 3 | ONE call end-to-end (not STT → separate LLM) — lock the technical integration story |  | ☐
39 | B | Sprint 3 | Expose get_player_stat(player, situation) with fuzzy name matching |  | ☐
40 | B | Sprint 3 | Situational filters: RISP, vs LHP, vs RHP, last 10, home/away |  | ☐
41 | C | Sprint 3 | Full live pipeline wired: audio → askGemma → stat_card event |  | ☐
42 | C | Sprint 3 | Latency logging per stage (audio_ms / gemma_ms / fn_ms / render_ms) |  | ☐
43 | C | Sprint 3 | Run 5 MLB fixtures end-to-end on device |  | ☐
44 | D | Sprint 3 | LiveStatCard fade-in animation <300ms |  | ☐
45 | D | Sprint 3 | FlashingCue orange pulse ~1Hz |  | ☐
46 | D | Sprint 3 | LatencyCounter bottom-right, real measured ms |  | ☐
47 | D | Sprint 3 | Medium-confidence variant: '~' prefix, amber, never TTS'd |  | ☐
48 | A | Sprint 4 | Voice-query prompt: transcript → intent → function-call → answer |  | ☐
49 | A | Sprint 4 | Add get_historical function (routes to Gemini if complex) |  | ☐
50 | A | Sprint 4 | 'I don't have verified data on that' escape when no function grounds confidently |  | ☐
51 | A | Sprint 4 | Enforce: TTS only on confidence=high |  | ☐
52 | B | Sprint 4 | Extend toolbox: get_team_stat, get_historical, get_game_context |  | ☐
53 | B | Sprint 4 | Situation-field parser (Gemma says 'vs lefties' → filter cache) |  | ☐
54 | B | Sprint 4 | Lock which demo queries must hit cloud (ideally zero — airplane mode) |  | ☐
55 | C | Sprint 4 | Press-to-talk capture up to 8s |  | ☐
56 | C | Sprint 4 | expo-speech TTS reply on high-confidence answers |  | ☐
57 | C | Sprint 4 | Haptic feedback on press/release |  | ☐
58 | D | Sprint 4 | VoiceQueryButton big-bottom with press-to-talk + haptic |  | ☐
59 | D | Sprint 4 | Listening state: waveform + 'Listening…' |  | ☐
60 | D | Sprint 4 | Thinking state: shimmer + 'Thinking…' |  | ☐
61 | D | Sprint 4 | AnswerCard with question at top, sourced answer, TTS indicator |  | ☐
62 | D | Sprint 4 | 'I don't have verified data' state — confident not apologetic |  | ☐
63 | A | Sprint 5 | Tiny eval harness: 10 inputs → expected outputs, rerun on prompt change |  | ☐
64 | A | Sprint 5 | Tighten stat_text brevity to ≤15 words |  | ☐
65 | A | Sprint 5 | Player-name echo suppression (don't repeat name broadcaster just said) |  | ☐
66 | B | Sprint 5 | Running score tracker (Bob Heussler ask) — cached PBP rolling window |  | ☐
67 | B | Sprint 5 | Story reminder queue (Rich Ackerman ask) — STT tracks spoken bullets |  | ☐
68 | B | Sprint 5 | Milestone/streak alerts (Trey Redfield ask) — at-risk flag at at-bat |  | ☐
69 | C | Sprint 5 | Airplane-mode dry run, all 3 features back-to-back, no restart |  | ☐
70 | C | Sprint 5 | Collect latency distribution — this number goes in the pitch |  | ☐
71 | D | Sprint 5 | Typography + spacing polish pass |  | ☐
72 | D | Sprint 5 | Airplane-mode status bar visible on every screen in demo build |  | ☐
73 | D | Sprint 5 | One hero frame per feature → screenshot for deck |  | ☐
74 | ALL | Sprint 6 | Feature freeze — no more prompt changes |  | ☐
75 | ALL | Sprint 6 | Dry run #1 timed, phone-only, airplane mode, no keyboard |  | ☐
76 | ALL | Sprint 6 | Dry run #2 same setup |  | ☐
77 | ALL | Sprint 6 | Dry run #3 run by different team member (stress test) |  | ☐
78 | D | Sprint 6 | Deck: 1 problem slide + 3 feature screens + latency number + Pat McCarthy quote |  | ☐
79 | D | Sprint 6 | Submission form draft: description, tagline, video link, team |  | ☐
80 | D | Sprint 6 | Upload backup demo video + spotting board PDF to submission |  | ☐
81 | ALL | Sprint 7 | Final rehearsal with stage setup (device + mirror) |  | ☐
82 | ALL | Sprint 7 | Assign 60s speaking parts per team member |  | ☐
83 | ALL | Sprint 7 | Rehearse kill-the-WiFi moment |  | ☐
84 | ALL | Sprint 7 | SUBMIT before 10:55 AM (not 11:00) |  | ☐

## Risks & Questions
⚠️ RISK REGISTER + OPEN QUESTIONS
RISKS
# | RISK | LIKELIHOOD | MITIGATION
1 | Cactus RN SDK doesn't expose Gemma 4 multimodal in JS | HIGH | Resolved in Sprint 0 spike. Fallback: Expo config plugin + native module glue wrapping the iOS Cactus SDK. One person owns this for duration.
2 | Sportradar rate limits (1 req/sec, 1000/month) | MEDIUM | Pre-fetch demo game ONCE to assets/game_cache.json. Zero Sportradar calls during live demo. All function calls resolve against local cache.
3 | Apple Developer provisioning / device trust fails | MEDIUM | Handled in Sprint 0 pre-work. iPhone signed in, dev mode on, trusted. Do not leave until hour 20.
4 | Gemma 4 multimodal latency >1.5s on iPhone | MEDIUM | Log per-stage latency from Sprint 3 onward. If >1.5s: downgrade to tiny variant, simplify prompt, trim function toolbox. Be honest in demo — real number beats fake.
5 | Gemma 4 prompt quality — stats wrong or irrelevant | HIGH | Build tiny eval harness in Sprint 5. Test every prompt change. Budget 3hrs of prompt tuning in Track A. Rule: '—' over guess, always.
6 | Stage WiFi at YC HQ unreliable | HIGH | Don't use it. Airplane mode from second 0 of demo. That's the whole pitch anyway — make the weakness into the moat.
7 | Physical demo failure (phone dies, cable flakes, mirror breaks) | MEDIUM | Backup video recorded Sprint 6, uploaded to Drive, cued in browser tab onstage. If live breaks, play the video.
8 | Team member burns out / crashes physically | HIGH | Mandatory sleep shifts: Shift A 12-4am, Shift B 4-8am, 2 people each. Nobody runs 22hrs straight.
9 | Judges ask 'did a broadcaster ask for Feature 3?' and the answer is awkward | MEDIUM | Pre-script the answer: lead with Pat McCarthy's statistician insight. Frame voice query as the statistician's tool that serves on-air talent. Honest > oversold.
10 | Sportradar stat missing for a key demo moment | MEDIUM | Pre-validate every demo stat manually in Sprint 4. Have backup stats pre-cached per demo beat in case one disappears.
OPEN QUESTIONS (resolve in Sprint 0)
# | QUESTION | OWNER | ANSWER
1 | Does Cactus RN SDK expose Gemma 4 multimodal audio input directly in JS? If no, who owns the Expo config plugin + native module route?
2 | Which specific Mets vs Phillies game do we pre-cache? (pick one with good audio clip available)
3 | Hardware puck for Feature 3 voice query, or on-screen button only? (on-screen = safer, puck = more cinematic)
4 | Who is the dedicated 'prompt tuner' in Track A for the 3hrs of iteration?
5 | Which team member owns the stage demo (speaks first, runs the device)?
6 | Is Gemini cloud routing allowed during the demo, or strict airplane-mode-only? (recommend: strict airplane mode)

## Success Criteria
🎯 SUCCESS CRITERIA & DEMO SCRIPT
MUST-HIT CRITERIA
CATEGORY | CRITERION | HOW WE PROVE IT IN THE DEMO
Feature 1 | Spotting board loads in airplane mode with ≥50 players, every stat carries Sportradar ✓ | Open the app with airplane mode on screen. Scroll through 50 players. Tap Soto. 'This took zero minutes — built overnight by Gemma 4 on Cactus, on device.'
Feature 2 | 30s MLB audio clip → stat card <1.5s with Sportradar ✓ and measured latency visible | Play the Mets clip. Stat card lands ~1s later. Point to the latency counter. 'Gemma 4 multimodal — audio in, function-calls Sportradar locally, stat out. Airplane mode.'
Feature 3 | Press button → voice question → sourced answer on screen + spoken <2s; knows when to decline | Press the puck: 'How does Soto hit against lefties this year?' Answer lands in ~1.5s + TTS. Bonus moment: ask something unsourceable, hear 'I don't have verified data on that.'
Trust | Every stat everywhere shows its source. One hallucinated stat kills the product. | Pan the camera across the board. Every ✓ visible. Narrate it: 'Every stat is Sportradar-verified. We say — not — when data is missing. A broadcaster's career is one wrong stat away from over.'
On-device moat | Full demo runs in airplane mode, no cables, no laptop, no backup WiFi | Airplane-mode indicator on the iOS status bar throughout the demo, clearly visible in the mirrored stage screen.
Venture-backable | Pitch closes with broadcaster research + market expansion vector | Open with Pat McCarthy quote. Close with: 'Broadcasters today, live field reporters next, any pro who needs the right info at the right moment after that.'
🎬 5-MINUTE DEMO SCRIPT
TIME | BEAT | WHAT HAPPENS ON SCREEN
0:00–0:30 | Problem + research | Title slide with Pat McCarthy quote. 'Broadcasters spend hours on prep, use 25%. We talked to 4 of them — NY Mets, Brooklyn Nets, CBS Sports Radio.'
0:30–1:30 | Feature 1: Spotting board | Open app (airplane mode visible). Tap Mets vs Phillies. Scroll 50 players. 'Zero minutes. Gemma 4 on Cactus, overnight, on device.'
1:30–3:00 | Feature 2: Live Whisper (money shot) | Play 30s MLB clip. Stat card lands ~1s. Latency counter shows real number. 'Audio in, function-calls local Sportradar cache, stat out. No cloud.'
3:00–4:00 | Feature 3: Voice Query | Press puck. 'How does Soto hit against lefties this year?' Answer + TTS ~1.5s. 'Color commentator or statistician — asks anything, gets sourced answers.'
4:00–5:00 | Pitch close | 'Broadcasters today, live reporters next, every pro needing the right info in the moment after that. Kill-the-WiFi is our moat. Every stat is sourced. That's how we earn trust in live media.'